## Bug Reports
CodePulse Blog Platform — Bug Report
Project: CodePulse ¦ Environment: Production (https://api.blog.munshinavid.me) ¦ Tool: Postman + Newman ¦ Date: June 2025
Bug ID | Title | Module | Endpoint | HTTP Method | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Evidence
BUG-001 | GET /me accessible without authentication | Auth | /api/Auth/me | GET | 1. Send GET /api/Auth/me request 2. Include NO cookie or Authorization header 3. Observe response | 401 Unauthorized — endpoint should require authentication | 200 OK — returns user identity data without any authentication cookie | High | High | Open | Newman run: 'No Cookie → GET /me' — Status 200, expected 401/403
BUG-002 | POST /Comments allows comment creation without authentication | Comments | /api/Comments | POST | 1. Send POST /api/Comments with valid body 2. Include NO cookie or Authorization header 3. Observe response | 401 Unauthorized — comments require a logged-in user | 200 OK — comment created successfully without any auth token | High | High | Open | Newman run: 'No Cookie → Create Comment' — Status 200, expected 401/403
BUG-003 | Tampered JWT token accepted by /me endpoint | Auth | /api/Auth/me | GET | 1. Login as Admin to get valid jwtToken 2. Modify the token value (append 'tampered') 3. Send GET /api/Auth/me with Cookie: jwtToken=<tampered_value> 4. Observe response | 401 Unauthorized — invalid signature should be rejected | 200 OK — endpoint returns user data with a cryptographically invalid token | Critical | Critical | Open | Newman run: 'Tampered Token → GET /me' — Status 200, expected 401/403
BUG-004 | Reader can delete comments belonging to other users | Comments | /api/Comments/{id} | DELETE | 1. Login as Reader A, create a comment 2. Login as Admin, create a separate comment 3. Login as Reader B (different reader) 4. Send DELETE /api/Comments/<Admin_comment_id> with Reader B cookie 5. Observe response | 403 Forbidden — only comment owner or Admin should be able to delete | 204 No Content — comment deleted successfully by unauthorized user | High | High | Open | Newman run: 'Unauthorized Comment Delete' — Status 204, expected 403
BUG-005 | Missing BlogPostId in comment body causes 500 instead of 400 | Comments | /api/Comments | POST | 1. Login as Reader 2. Send POST /api/Comments with body: {"content": "test"} (BlogPostId omitted) 3. Observe response | 400 Bad Request — [Required] DataAnnotation should return validation error | 500 Internal Server Error — unhandled exception instead of validation response | Medium | Medium | Open | Newman run: 'Create Comment — Missing BlogPostId' — Status 500, error: 'An error occurred while s...'
BUG-006 | GET /BlogPosts/{id} returns 500 instead of 404 for missing post | Posts | /api/BlogPosts/{id} | GET | 1. Send GET /api/BlogPosts/00000000-0000-0000-0000-000000000099 2. Post with this ID does not exist 3. Observe response | 404 Not Found — standard REST convention for missing resource | 500 Internal Server Error — generic Exception('Blog post not found') caught by GlobalExceptionHandler | Low | Low | Open | Newman run: 'Get Post by ID — Not Found' — Status 500 (documented as known behavior)

## Test Cases
CodePulse Blog Platform — Test Case Document
Project: CodePulse ¦ Environment: Production ¦ Tool: Postman + Newman ¦ Total: 50 Test Cases
TC ID | Module | Test Scenario | Precondition | Test Steps | Test Data | Expected Result | Actual Result | Status | Type | Priority
TC-001 | Auth | Register with valid credentials | API is running | 1. POST /api/Auth/register 2. Provide valid email and password | {"email":"newuser@test.com","password":"password123"} | 200 OK — registration successful | 200 OK | Pass | Positive | High
TC-002 | Auth | Register with duplicate email | User already registered | 1. POST /api/Auth/register 2. Use already-registered email | {"email":"existing@test.com","password":"pass123"} | 400 Bad Request — DuplicateUserName identity error | 400 Bad Request | Pass | Negative | High
TC-003 | Auth | Register with missing email field | None | 1. POST /api/Auth/register 2. Omit email field | {"password":"pass123"} | 400 Bad Request — Email is required | 400 Bad Request | Pass | Negative | High
TC-004 | Auth | Register with missing password field | None | 1. POST /api/Auth/register 2. Omit password field | {"email":"test@test.com"} | 400 Bad Request — Password is required | 400 Bad Request | Pass | Negative | High
TC-005 | Auth | Register with password shorter than 6 chars | None | 1. POST /api/Auth/register 2. Provide 3-char password | {"email":"test2@test.com","password":"abc"} | 400 Bad Request — password too short | 400 Bad Request | Pass | Negative | Medium
TC-006 | Auth | Register with empty body | None | 1. POST /api/Auth/register 2. Send empty JSON body {} | {} | 400 Bad Request — multiple required field errors | 400 Bad Request | Pass | Negative | Medium
TC-007 | Auth | Login with valid Admin credentials | Admin account exists | 1. POST /api/Auth/login 2. Provide admin email and password | {"email":"admin@myblog.com","password":"1234"} | 200 OK — returns email, roles, sets jwtToken cookie | 200 OK | Pass | Positive | High
TC-008 | Auth | Login with valid Reader credentials | Reader account exists | 1. POST /api/Auth/login 2. Provide reader email and password | {"email":"reader@test.com","password":"password123"} | 200 OK — returns Reader role in response | 200 OK | Pass | Positive | High
TC-009 | Auth | Login with invalid credentials | None | 1. POST /api/Auth/login 2. Provide wrong password | {"email":"admin@myblog.com","password":"wrongpass"} | 400 Bad Request — Invalid Email or Password | 400 Bad Request | Pass | Negative | High
TC-010 | Auth | GET /me returns identity for authenticated user | Admin logged in | 1. Login as Admin 2. GET /api/Auth/me with cookie | Cookie: jwtToken=<valid_token> | 200 OK — returns userId, email, roles | 200 OK | Pass | Positive | High
TC-011 | Auth | GET /me without cookie returns 200 (BUG-001) | None | 1. Send GET /api/Auth/me 2. No cookie attached | No auth header or cookie | 401 Unauthorized (EXPECTED) — returns 200 OK (ACTUAL BUG) | 200 OK | Fail | Security | Critical
TC-012 | Auth | Logout clears session | User logged in | 1. Login 2. POST /api/Auth/logout | Cookie: jwtToken=<valid_token> | 200 OK — cookie cleared | 200 OK | Pass | Positive | Medium
TC-013 | Categories | Create category with valid data | Admin logged in | 1. POST /api/Categories 2. Provide name and urlHandle | {"name":"Technology","urlHandle":"technology"} | 200 OK — returns category with id, name, urlHandle | 200 OK | Pass | Positive | High
TC-014 | Categories | Get all categories | At least one category exists | 1. GET /api/Categories | None | 200 OK — returns array of categories with id, name, urlHandle | 200 OK | Pass | Positive | High
TC-015 | Categories | Get category by valid ID | Category exists | 1. GET /api/Categories/{id} | Valid GUID | 200 OK — returns matching category | 200 OK | Pass | Positive | Medium
TC-016 | Categories | Get category by non-existent ID | None | 1. GET /api/Categories/00000000-0000-0000-0000-000000000000 | All-zero GUID | 404 Not Found | 404 Not Found | Pass | Negative | Medium
TC-017 | Categories | Update category | Category exists, Admin logged in | 1. PUT /api/Categories/{id} 2. Provide updated name | {"name":"Tech Updated","urlHandle":"tech-updated"} | 204 No Content | 204 No Content | Pass | Positive | Medium
TC-018 | Categories | Delete category | Category exists, Admin logged in | 1. DELETE /api/Categories/{id} | Valid GUID | 204 No Content | 204 No Content | Pass | Positive | Medium
TC-019 | Categories | Invalid GUID format in route | None | 1. GET /api/Categories/not-a-valid-guid | non-GUID string | 400 Bad Request or 404 | 404 Not Found | Pass | Negative | Low
TC-020 | Posts | Create blog post with all required fields | Admin logged in, category exists | 1. POST /api/BlogPosts 2. Provide title, content, urlHandle, author, categoryIds | {"title":"Test","content":"Body","urlHandle":"test-post","author":"Admin","categoryIds":[]} | 200 OK — returns complete blog post schema | 200 OK | Pass | Positive | High
TC-021 | Posts | Create post — missing Title (FluentValidation) | Admin logged in | 1. POST /api/BlogPosts 2. Omit title field | Body without title | 400 Bad Request — 'Title is required' | 400 Bad Request | Pass | Negative | High
TC-022 | Posts | Create post — missing Content (FluentValidation) | Admin logged in | 1. POST /api/BlogPosts 2. Omit content field | Body without content | 400 Bad Request — 'Content is required' | 400 Bad Request | Pass | Negative | High
TC-023 | Posts | Create post — missing UrlHandle (FluentValidation) | Admin logged in | 1. POST /api/BlogPosts 2. Omit urlHandle field | Body without urlHandle | 400 Bad Request — 'UrlHandle is required' | 400 Bad Request | Pass | Negative | High
TC-024 | Posts | Create post — missing Author (FluentValidation) | Admin logged in | 1. POST /api/BlogPosts 2. Omit author field | Body without author | 400 Bad Request — 'Author is required' | 400 Bad Request | Pass | Negative | High
TC-025 | Posts | Create post — all 4 required fields empty | Admin logged in | 1. POST /api/BlogPosts 2. Send all required fields as empty strings | {"title":"","content":"","urlHandle":"","author":""} | 400 Bad Request — all 4 validation errors present | 400 Bad Request | Pass | Negative | High
TC-026 | Posts | Create post — invalid JSON body | Admin logged in | 1. POST /api/BlogPosts 2. Send malformed JSON | not-json-at-all | 400 Bad Request — JSON parse error | 400 Bad Request | Pass | Negative | Medium
TC-027 | Posts | Create post — wrong type for IsVisible | Admin logged in | 1. POST /api/BlogPosts 2. Send isVisible as string | {"isVisible":"yes"} | 400 Bad Request — type mismatch error | 400 Bad Request | Pass | Negative | Medium
TC-028 | Posts | Get all posts (public, paginated) | Posts exist | 1. GET /api/BlogPosts?page=1&pageSize=10 | page=1, pageSize=10 | 200 OK — paged result with data array and total count | 200 OK | Pass | Positive | High
TC-029 | Posts | Get all posts — with search query | Posts exist | 1. GET /api/BlogPosts?query=Angular&page=1&pageSize=5 | query=Angular | 200 OK — filtered results matching query | 200 OK | Pass | Positive | Medium
TC-030 | Posts | Get admin post listing (includes drafts & deleted) | Admin logged in | 1. GET /api/BlogPosts/admin?page=1&pageSize=10 | Admin cookie | 200 OK — includes all posts regardless of status | 200 OK | Pass | Positive | High
TC-031 | Posts | Reader cannot access admin post listing | Reader logged in | 1. Login as Reader 2. GET /api/BlogPosts/admin | Reader cookie | 403 Forbidden | 403 Forbidden | Pass | Security | High
TC-032 | Posts | Get post by valid ID | Post exists | 1. GET /api/BlogPosts/{id} | Valid post GUID | 200 OK — full blog post with readingTimeMinutes | 200 OK | Pass | Positive | High
TC-033 | Posts | Get post by ID — not found returns 500 (BUG-006) | None | 1. GET /api/BlogPosts/00000000-0000-0000-0000-000000000099 | Non-existent GUID | 404 Not Found (EXPECTED) — returns 500 (ACTUAL BUG) | 500 Internal Server Error | Fail | Negative | Low
TC-034 | Posts | Soft-delete blog post | Post exists, Admin logged in | 1. DELETE /api/BlogPosts/{id} | Valid post GUID | 204 No Content — post soft-deleted | 204 No Content | Pass | Positive | High
TC-035 | Posts | Restore soft-deleted post | Post is soft-deleted, Admin logged in | 1. PUT /api/BlogPosts/restore/{id} | Valid post GUID | 200 OK — post restored | 200 OK | Pass | Positive | High
TC-036 | Posts | Hard-delete blog post | Post exists, Admin logged in | 1. DELETE /api/BlogPosts/hard-delete/{id} | Valid post GUID | 200 OK — post permanently deleted | 200 OK | Pass | Positive | High
TC-037 | Posts | Get dashboard stats | Admin logged in | 1. GET /api/BlogPosts/stats | Admin cookie | 200 OK — total, published, draft, deleted counts | 200 OK | Pass | Positive | Medium
TC-038 | Posts | Reader cannot access dashboard stats | Reader logged in | 1. Login as Reader 2. GET /api/BlogPosts/stats | Reader cookie | 403 Forbidden | 403 Forbidden | Pass | Security | High
TC-039 | Images | Upload image without file — expect 400 | None | 1. POST /api/Images/upload 2. Send empty multipart body | No file attached | 400 Bad Request | 400 Bad Request | Pass | Negative | Medium
TC-040 | Images | Get all uploaded images | Images exist | 1. GET /api/Images | None | 200 OK — array of image objects | 200 OK | Pass | Positive | Medium
TC-041 | Comments | Add comment as authenticated Reader | Reader logged in, post exists | 1. Login as Reader 2. POST /api/Comments with content and blogPostId | {"content":"Great post!","blogPostId":"<valid_id>"} | 200 OK — comment created with id, content, user info | 200 OK | Pass | Positive | High
TC-042 | Comments | Add comment without authentication (BUG-002) | None | 1. POST /api/Comments with valid body 2. No cookie attached | No auth cookie | 401 Unauthorized (EXPECTED) — returns 200 OK (ACTUAL BUG) | 200 OK | Fail | Security | High
TC-043 | Comments | Get comments by blog post ID | Comments exist for post | 1. GET /api/Comments/post/{blogPostId} | Valid post GUID | 200 OK — array of comments | 200 OK | Pass | Positive | Medium
TC-044 | Comments | Delete comment by owner | Reader owns comment | 1. Login as comment owner 2. DELETE /api/Comments/{commentId} | Valid comment GUID, owner cookie | 204 No Content | 204 No Content | Pass | Positive | High
TC-045 | Comments | Delete comment by Admin (not owner) | Admin logged in, comment exists | 1. Login as Admin 2. DELETE /api/Comments/{commentId} (Admin not comment owner) | Admin cookie, comment GUID | 204 No Content — Admin override allowed | 204 No Content | Pass | Positive | High
TC-046 | Comments | Reader deletes another user's comment (BUG-004) | Two Reader accounts | 1. Login as Reader A, add comment 2. Login as Reader B 3. DELETE Reader A's comment with Reader B cookie | Reader B cookie, Reader A comment GUID | 403 Forbidden (EXPECTED) — returns 204 No Content (ACTUAL BUG) | 204 No Content | Fail | Security | High
TC-047 | Comments | Delete non-existent comment | None | 1. DELETE /api/Comments/00000000-0000-0000-0000-000000000000 | All-zero GUID | 404 Not Found | 404 Not Found | Pass | Negative | Medium
TC-048 | Comments | Create comment — missing Content | Reader logged in | 1. POST /api/Comments 2. Omit content field | {"blogPostId":"<valid_id>"} | 400 Bad Request — Content is required | 400 Bad Request | Pass | Negative | Medium
TC-049 | Comments | Create comment — missing BlogPostId (BUG-005) | Reader logged in | 1. POST /api/Comments 2. Omit blogPostId field | {"content":"test"} | 400 Bad Request (EXPECTED) — returns 500 Internal Server Error (ACTUAL BUG) | 500 Internal Server Error | Fail | Negative | Medium
TC-050 | Comments | Tampered token accepted by /me (BUG-003) | None | 1. Get valid jwtToken from login 2. Modify token string 3. GET /api/Auth/me with tampered cookie | Cookie: jwtToken=<tampered_value> | 401 Unauthorized (EXPECTED) — returns 200 OK (ACTUAL BUG) | 200 OK | Fail | Security | Critical

## Summary
QA Portfolio — Test Execution Summary
NEWMAN AUTOMATED RUN
Total Requests | 79 |  | Total Assertions | 112
Passed Assertions | 106 |  | Failed Assertions | 6
Pass Rate | 94.6% |  | Run Duration | 31.2s
Avg Response Time | 104ms |  | Data Received | 63.31 kB
TEST CASE DOCUMENT
Total Test Cases | 50 |  | Passed | 44
Failed (Bugs Found) | 6 |  | Pass Rate | 88%
BUG SUMMARY
Bug ID | Title | Severity | Status
BUG-001 | GET /me accessible without auth | High | Open
BUG-002 | POST /Comments without auth | High | Open
BUG-003 | Tampered token accepted by /me | Critical | Open
BUG-004 | Reader deletes other user comment | High | Open
BUG-005 | Missing BlogPostId → 500 not 400 | Medium | Open
BUG-006 | Post not found → 500 not 404 | Low | Open